## questions
Questions and remarks on Preliminary Safety Evluation Criteria
N° | Scope | Doc. | Question | Comments | Answer/Comment/Remark
1 | deliverables | Safety process | Is the SSRS identified in the WP2 deliverables? |  | The SSRS is not yet part of any Deliverable, so it is hard to name it correctly.
2 | deliverables | Documentation liste | What is th PIEm, identified as the 3rd deliverable to be issued within WP3? |  | Could you name the exact localtion of this point in the document?
3 |  | Safety process | The Safety Case is usualy presented aside from the other Safety or V&V documentation, whether it usualy gathered all these document in the final Safety Case report. Is this Safety Case described in the D4.2 correspond to the RAMS Case? |  | It is the Plan, that the safety Plan is one part of the D4.2
4 |  | Safety process | What do you mean by system concept? |  | This refereve to the first step of the EN 50126 lifecycle
5 | Sub-System Hazard Analysis | Safety process - §1.3, table1 | The Sub-System Hazard Analysis should consider the following inputs: - The Manufacturers know How on External Hazards (Railway crash scenarii, systematic system failures, holes in common protection barriers...) - The final user's needs specifications, - External System Specifications and Constraints - The operating rules - The Subsets 088 and 091 Preliminary Hazard Analysis from System Requirement Specification. Actually, a lot of information will be taken without change from subset91 to PHA, and mostly the scope of what will be considered will change between both documents. - The Safety case goals (mostly provided with user's need specifications and External Specifications and Constraints) | This document corresponds to the System Hazard Analysis plus the Sub-System Hazard analysis. The real Preliminary Hazard Analysis related to our scope of work are both subset88&91. The work would be to refine this document to our scope: OBU EVC Kernel for the soft part | All this points are correct and have to be incorporated in the safety plan, but they are to specific for the criteria on the tool decision (short version incorporated in the section 1.4)
6 | Sub-System Hazard Analysis | Safety process - §1.3, table1 | The Sub-System Hazard Analysis outputs to be considered are: - the list of Safety functions identified, associated with their Safety Criteria (several Criterii for one function). These Safety functions have to be used in the System Safety Analysis. - The list of Safety Constraints on System Architecture - the list of Hazardeous situations (for the Hazard log) | same | All this points are correct and have to be incorporated in the safety plan, but they are to specific for the criteria on the tool decision (short version incorporated in the section 1.4)
7 | System Safety Analysis | Safety process - §1.3, table1 | The System Safety Analysis should deal with the following inputs: - The final user's needs specifications, - External System Specifications and Constraints - Internal System Specifications - Safety functions and associated criteria defined in the previous Preliminary Hazard Analysis - Safety constraints identified in the previous SHA. |  | What is the differenz between the hazard and the safety analysis? All this points are correct and have to be incorporated in the safety plan, but they are to specific for the criteria on the tool decision (short version incorporated in the section 1.4)
8 | System Safety Analysis | Safety process - §1.3, table1 | The System Safety Analysis should provide the following outputs: - the traceability matrix between Security functions and structures (at system level, and provide it for the Sub-System Safety Analysis) - The list of Structures (part of architecture hosting a global or part of Safety function) associated with the related protections (this information is sent to the SSRS) - The list of residual hazardeous situation (to fill the backlog, = list of Hazardous situation identified in APR - hazardous situations covered and protected by system architecture or barriers). |  | What is the differenz between the hazard and the safety analysis? All this points are correct and have to be incorporated in the safety plan, but they are to specific for the criteria on the tool decision (short version incorporated in the section 1.4)
9 | Sub-System Safety Analysis | Safety process - §1.3, table1 | This document that would support this activity is the Sub-System Safety Analysis. It is entirely based on the Sub-System Hazard Analysis, and would consider the realization of the following tasks: - Refinement of Safety functions identified in Preliminary Hazard assessment into safety sub-functions. - The list of associated Safety Requirements Specifications at both System and Sub-System level - The list of residual hazardeous situation issued from the Sub-System | As Open ETCS SSRS scope has been quite reduced (OBU EVC Kernel only), we can foresee a merge between System and Sub-System Safety Analysis. It would be easier to meet a decision once the work will be started. | Is already planed this way (see section 1.4)
10 | Safety Activity | Safety process - §1.3, table1 | Is the Risk Assessment presented in the table a specific document? For me, it can be considered as either part of the Sub-System Safety analysis, either part of the Safety log (and so provided in the final Safety Case document). But makes sense to treat it aside, in order to define more precisely the data flows and the steps succession in Open ETCS. |  | That was the reason
11 | Safety Activity | Safety process - §1.3, table1 | Same remark, this artifact is, to me, one of the major point of the SSHA. But at it is integrated in a specific workflow, it is worthy to insulate it in the table. |  | That was the reason
12 | Safety Activity | Safety process - §1.3, table1 | The Safety Acceptance Criteria are defined in the Preliminary Hazard Assessment, and normaly defined straight from the Users System specifications requirements (output: safety criteria associated to the Safety functions). This is a proority work regarding Safety in the project OpenETCS? |  | Incorporated in section 1
13 | Safety Activity | Safety process - §1.3, table1 | The Safety related Functionnal requirements (as we do consider in the Open ETCS project that System Safety Analysis are considered as input) have to be treated in the Sub-System Safety Analysis. They are corresponding to the output list of Safety Requirments Specifications at system level. |  | That is correct, but we are not dealing with the system level overall. It was isolated from the pure requirements to demonstrated the additional work, but it can be merged. (changed in section 1.4)
14 | Safety Activity - Safety Plan | Safety process - §1.3, table1 | The major input for the Safety plan are not safety related documentation of the project. The following inputs can be considered: - QAP - Project documentation (FPP, …) For me, the Safety plan shal describe all Safety Case organization, but not especially provide input to the documents handled within this Safety Case. Of course the Safety Log and the Safety Case have to be described in it, but I would preconize to fill the Safety Plan outputs this way: "the Safety Case Structure, organisation, and tooling" more than saying the Safety Case + the Hazard Log. |  | Added activity "Establish safety plan" considering the inputs
15 |  | Safety process - §1.3, figure 2 | About the SSRS IO with the Safety documentation, I have the following points: - The main inputs for the SSRS are the subset26 and the operating rules. Maybe the FIS could be added, as interoperability is a major point. The V&V provides its results too (these results are gathered in the Hazard log at the same time) at the end of the related verification activities on this document. |  | FISis included in the figure 2, but I'm not sure that the V&V inputs are actually the hazard log, but I incorporated it, too.
16 |  |  | The table 3 given in the §1.4 looks very similar to the table1. Maybe we could focus more on the content than on the IO already described |  | I canceled out the generell I&O table and just left the list of activities, while extending the OpenETCs specific table